## RR Template
Housing Element Program Name/Number |  | Program Description and Objective | Timeframe and Achievements | Program Evaluation and Recommendation
Goal 1 Promote New Housing Development
1-1A | Inventory Vacant and Underutilized Land and Progress toward the RHNA. Ensure Land Use Policies will Enable Accomplishment of RHNA Goals. | Annually update the inventory of vacant and underutilized parcels. In addition, annually review the composition of the housing stock as well as of units under construction or expected to be constructed during the planning period. Compare this analysis to the City’s Regional Housing Needs Allocation (RHNA) to determine if any changes in land use policy are warranted to ensure an adequate supply of land to meet RHNA target of 373 very low income, 268 low income, 315 moderate income, and 679 above moderate units. | Due to the elimination of the Redevelopment Agency this task was not completed. | Long title - better way to say this?
1-2A | Implement the Inclusionary Housing Ordinance | Continue to implement the Inclusionary Housing Ordinance with the aim of constructing 40 low-income and 60 moderate-income units by 2014. | Goal 40 low-income/60 moderate income by 2014; Park Station constructed in 2007 resulted in 7 new low-income units and 8 new moderate income units.
1-3A | Investigate a Commercial Linkage Fee for Affordable Housing | By 2010, investigate the feasibility of a commercial linkage fee to support affordable housing. | The City continues to explore funding options for affordable housing. As part of the 21 Elements group Cities are looking at cost to share in a nexus study for a commercial linkage fee to support affordable housing.
1-4A | Acquire Sites for Affordable Housing Development | The Redevelopment Agency shall acquire or work with nonprofit housing developers to acquire vacant or underutilized land or sites with blighted and/or nonconforming uses to ensure sufficient capacity for the development of 60 affordable housing units by 2014. | During this housing cycle (2007-2014) the Redevelopment Agency acquired property within the El Camino Real/Chestnut Avenue Area Plan and in the Downtown area. The City continues to work with developers on potential projects. However, due to dissolution of the Redevelopment Agency in 2011, funding for property acquisition is limited and the future depends on the ultimate outcome of the Successor Agency to the Redevelopment Agency.
1-4B | Consult with Non-Profit Housing Developers to Identify Development Opportunities | The Redevelopment Agency shall continue to meet with nonprofit housing developers annually to discuss and identify development opportunities, including opportunities for the reuse of publicly-owned parcels, for affordable housing. | Policy 1-4 Achievements above.
1-4C | Pursue Funding and Support Funding Applications for Affordable Housing | The Redevelopment Agency shall continue to apply on an annual basis for federal and State funds to promote the development of affordable housing and support funding applications by non profit housing developers. | Policy 1-4 Achievements above.
1-4D | Consider Fee Waivers for Affordable Housing | Continue to consider waiver of fees on a case by case basis for affordable housing development. | Policy 1-4 Achievements above.
1-5A | Complete the Comprehensive Zoning Ordinance Update | By December 2009, complete the Comprehensive Zoning Ordinance Update to ensure consistency with General Plan policies, appropriate zoning for the Housing Opportunity Sites, and incorporation of the tools and flexibility needed to encourage: 1) a variety of unit sizes; 2) a mix of housing types; 3) mixed use development; and 4) more intense mixed use development in the South El Camino Real corridor. Measures to accomplish these goals include expanding permissions for residential and mixed use development in new areas, Design Guidelines and an EIR for a General Plan Amendment for the South El Camino Real corridor, and potentially reducing parking requirements for areas near transit. In addition, the Update will designate a district where an emergency shelter is permitted by right and subject only to the same development and management standards applicable to other uses in the zone. It will also ensure that transitional and supportive housing are subject only to those restrictions that apply to other residential uses of the same type in the zone. | Updated Zoning Ordinance was adopted August 2010.
1-6A | Review the Density Bonus Ordinance | By December 2009 and in conjunction with the Comprehensive Zoning Ordinance Update, review the Density Bonus Ordinance and make modifications as necessary to construct 50 additional units by 2014 and for consistency with State law. | SSFMC 20.380-Inclusionary Housing Regulations was updated to be consistent with State law as part of the comprehensive Zoning Ordinance update adopted in August 2010. (How does this related to the Density Bonus Ordinance?)
1-7A | Increase Residential Densities in Downtown | Explore increased residential densities and modified development standards for parcels in the downtown area to support the objectives of the Downtown Strategy and General Plan policies. | The Zoning Ordinance was updated in 2010 and includes changes that encourage a mix of residential, commercial and office uses in the Downtown and near transit. In 2012 the City received a grant and began work on the Downtown Station Area Land Use Plan that will also explore increased densities near the Caltrain Station; this project is targeted for completion/adoption by June 2014. (Seems like this also relates to program 1-5A.)
1-8A | Support the development of secondary dwelling units | Support and facilitate the development of second units on single-family designated and zoned parcels with the goal of developing 20 second units by 2014. | Brochures are provided at the Permit Center Counter; in addition staff explores second unit options during counter discussions and during building permit plan checks. A total of 7 second units have been constructed from 2007-2012 (2 for the 2012 calendar year) and have been recorded with the County to reflect the legal second unit. | The HE shows a time frame of December 2009, but an objective of developing these units by 2014. Is there some sort of policy revision or other item that is missing from this program description that should have the 2009 timeframe?
1-8B | Promote Second Dwelling Unit Education | Actively promote community education on second units by posting information on the City’s website and providing brochures at the One Stop Permit Center public counter. | See Policy 1-8 Achievements above.
1-9A | Identify Residential Development Opportunities on Infill and Underutilized Sites | Identify residential development opportunities on infill and underutilized sites as part of the Zoning Ordinance update, South El Camino Real General Plan update, and the El Camino Real / Chestnut Specific Plan process. | The South El Camino Real Plan was adopted in April 2010 and the El Camino Real/Chestnut Area Plan was adopted in May 2011 to promote infill and redevelopment projects.
Goal 2 Remove Constraints to Housing Development
2-1A | Provide Support for Private Market Construction through Expedited Review and Other Means | Support private market construction by:  working with property owners, project sponsors, and developers to expedite the permit review process;  designing housing projects that meet the goals, objectives and policies of this Housing Element;  providing timely assistance and advice on permits, fees, environmental review requirements, and affordable housing agreements to avoid costly delays in project approval; and  interfacing with community groups and local residents to ensure public support for major new housing developments. | The One Stop Permit center continues to provide accessible services by Planning, Building and Public Works in one building. The One Stop Permit Center hours are from 8am-5pm. Permit processing is efficient and timely, with accessible staff. Our Planning Commission meets twice a month and our Design Review Board meets once a month to ensure the timely processing of applications. | Is this supposed to suggest that the City will be designing projects or that it will somehow be supporting the design of projects?
POL 2-2 | Ensure Adequate Public Facilities | Ensure the availability of adequate public facilities, including streets, water, sewerage, and drainage, throughout the residential areas of the City in order to encourage residential development to support population growth and fulfill improvement commitments. | On specific development projects the City collects "sewer impact fees" to help support the ongoing maintenance and upgrading of the City's infrastructure. The City of SSF adopted a CIP budget of approximately $99million dollars for fiscal year 2011-2012, and a CIP budget of approximately $33 million dollars for fiscal year 2012-2013, with several projects slated for the repair and upgrade of infrastructure to support added populations. | There was no Program 2-2A, so I've included the Policy in case the jurisdiction would like to address it in their review. -- NOTE: There are quite a few instances (like this one) where this happens and the policy is specific enough and addresses an objective that has no parallel in the programs. Where the policy is redundant with a program, I have indicated as much.
2-3A | Advance the Housing Revenue Bond and Mortgage Credit Certificate Programs | Cooperate with the County to implement its Housing Revenue Bond and Mortgage Credit Certificate programs with the goal of assisting 20 moderate income households with home purchases. | The City continues to participate in the 21 Elements TAC meetings. The City also collaborates with HEART (Housing Endowment and Regional Trust) of San Mateo County as well as the Housing Leadership Council of San Mateo County. The Housing Rehab Bond and Mortgage Credit Certificate Programs were not utilized because the new construction of the Park Station project (2007) had purchase prices so low that it was to necessary to implement these programs.
2-4A | Implement Design Guidelines | By 2010, implement design guidelines as part of the Zoning Ordinance update in order to ensure that new development promotes quality design and harmonizes with existing neighborhood surroundings. | Residential Design Guide was adopted by the Planning Commission by Resolution No. 2471. In addition, the recently adopted El Camino Real/Chestnut Avenue Plan includes Design Standards and Guidelines.
POL 2-5 | Support Excellent Design & CEQA Review While Ensuring Expeditious Permit Processing | Support excellent design through the continued use of the design review board and/or staff as well as adherence to CEQA while ensuring an efficient process. | Our Design Review Board meets once a month to provide comments on new construction and additions to residential development. | There was no Program 2-5A, so I've included the Policy in case the jurisdiction would like to address it in their review.
2-6A | Disseminate Affordable Housing Program Information | Update the City's website to include information on affordable housing, housing programs, and inclusionary units. | The City continually provides material to the public regarding affordable housing programs and inclusionary units including at the City's Community Learning Center, on our community calendars, on the City's website, and at our Citizen's Academy. We also regularly send information to local non-profits that serve low income residents in SSF, including the North Peninsula Neighborhood Services Center. The Housing and Community Development Department provides the public with affordable housing resource packets that contain specific information on how to find affordable housing programs, along with listings of affordable housing locations and properties with open wait lists.
Goal 3 Conserve Existing Housing & Neighborhoods
POL 3-1 | Encourage Private Residential Reinvestment in Older Neighborhoods | Encourage private reinvestment in older residential neighborhoods and private rehabilitation of housing. | The Department of Housing and Community Development manages Community Development Block Grants (CDBG) Programs which provides funding to Rebuilding Together Peninsula (RTP). RTP rehabilitates housing in older neighborhoods. Project funding ranges from replacement of water heaters to the repair of leaky roofs. (Is this private investment?) | There was no Program 3-1A, so I've included the Policy in case the jurisdiction would like to address it in their review.
3-2A | Fund Lower Income Housing Rehabilitation | By 2014, provide funds to assist 40 very low and low income owner and renter households to undertake repairs and maintain their dwellings as viable units. | CDBG funds were used for the following housing rehabilitation activities • City sponsored Housing Rehab Program FY 12-13: o Issued 3 Housing Rehab Loans o Issued 3 emergency home repair vouchers o Issued 2 debris box vouchers o Covered emergency gas/sewer line repairs at 7 city-owned affordable rental units • Center for Independence of Individuals with Disabilities (CID) – The City uses CDBG funds to support CID’s Housing Accessibility Modification (HAM) Program. FY 12-13 the HAM program has provided accessibility modifications to 8 South San Francisco households. • Rebuilding Together Peninsula (RTP) – The City uses CDBG funds to support two RTP programs: National Rebuilding Day and Safe at Home. FY 12-13 the two programs provided free home repairs to 18 South San Francisco households; • North Peninsula Neighborhood Services Center (NPNSC) House Helpers – Although NPNSC disbanded this program in December 2012, the program did provide free home repairs to 9 South San Francisco households.
POL 3-3 | Prioritize Funding for Acquisition and Rehabilitation of Lower Income Units in Older Neighborhoods | Prioritize Federal, State and Redevelopment Agency funds for the acquisition and rehabilitation of units in older residential neighborhoods that house low income families earning less than 80 percent of the Area Median Income (AMI). | (Repeats above.) CDBG funds were used for the following housing rehabilitation activities • City sponsored Housing Rehab Program FY 12-13: o Issued 3 Housing Rehab Loans o Issued 3 emergency home repair vouchers o Issued 2 debris box vouchers o Covered emergency gas/sewer line repairs at 7 city-owned affordable rental units • Center for Independence of Individuals with Disabilities (CID) – The City uses CDBG funds to support CID’s Housing Accessibility Modification (HAM) Program. FY 12-13 the HAM program has provided accessibility modifications to 8 South San Francisco households. • Rebuilding Together Peninsula (RTP) – The City uses CDBG funds to support two RTP programs: National Rebuilding Day and Safe at Home. FY 12-13 the two programs provided free home repairs to 18 South San Francisco households; • North Peninsula Neighborhood Services Center (NPNSC) House Helpers – Although NPNSC disbanded this program in December 2012, the program did provide free home repairs to 9 South San Francisco households. | There was no Program 3-3A, so I've included the Policy in case the jurisdiction would like to address it in their review.
3-4A | Enforce Housing, Building and Safety Codes | Continue to aggressively enforce uniform housing, building, and safety codes. | The City operates a Code Enforcement Division through the Fire Department. For 2012 there were 5 enforcement officers on staff that enforce housing, building and safety codes. Building Division staff enforces these codes as well when they are out on inspections. Incompatible uses are addressed in zoning code section 20.320.
3-4B | Eliminate Blight in Residential Neighborhoods | Seek to eliminate incompatible land uses and blight in residential neighborhoods through targeted code enforcement and other available regulatory measures. | See Policy 3-4 Achievements above.
3-5A | Create a Capital Improvement Program for Older Neighborhoods | Create a capital improvement program to upgrade and keep in good repair housing, streets, sidewalks, and other municipal systems in older neighborhoods such as Village Way, Willow Gardens, Town of Baden, Downtown (Old Town), Irish Town, and Peck’s Lots. | The City of SSF adopted a CIP budget of approximately $99 million dollars for fiscal year 2011-2012, and a CIP budget of approximately $33 million dollars for fiscal year 2012-2013, with projects set for street repairs and sidewalk and municipal upgrades in the older residential neighborhoods of SSF.
POL 3-6 | Ensure High Quality Design in Rehabilitation | Ensure that rehabilitation efforts promote quality design and harmonize with existing neighborhood surroundings. | Planning Commission Resolution No. 2471 adopted the Design Review Guide for residences and additions to homes in SSF. Staff works with architects and home owners to ensure that proposed designs complement and blend in with the character of the existing neighborhood. In addition, staff consults the City's historic resource list to ensure that any design changes are consistent with the architectural character of existing historic structures. | There was no Program 3-6A, so I've included the Policy in case the jurisdiction would like to address it in their review.
3-7A | Provide Low Interest Loans for Housing Rehabilitation | Provide low-interest loans for rehabilitation of single-family and multi-family housing through the Housing Rehabilitation Program and with CDBG funds. Give priority to homes in the Downtown Target Area with a goal of rehabilitating 40 units by 2014. | CDBG Housing Rehab Loan Program issued 1 loan during FY 11-12 and 3 loans to date during FY 12-13.
3-7B | Work with the Housing Authority to Preserve Public Housing | The City shall support the South San Francisco Housing Authority in the continued operation and rental of 80 units of public housing. | See Policy 3-7 Achievements above.
3-8A | Improve and Preserve Boarding Houses and SRO Developments | Provide financial assistance for physical improvements to boarding houses and single room occupancy developments in the Downtown area in order to ensure preservation of these resources. | There have been no loans/grants issued in 2012 for the preservation or improvement to existing boarding houses or SROs.
3-9A | Enforce Condominium Conversion Limitations | Continue to enforce limits on the conversion of apartment units to condominiums. As specified in Chapter 19.80 of the Municipal Code, condominium conversions are allowed only if they meet the following general criteria: a. A multiple-family vacancy rate of at least five percent exists; b. The conversion has an overall positive effect on the City’s available housing stock; c. Adequate provisions are made for maintaining and managing the resulting condominium projects; d. The project meets all building, fire, zoning, and other applicable codes in force at the time of conversion; and e. The conversion is consistent with all applicable policies of the General Plan. | SSFMC section 19.80 sets forth the regulations for condominium conversions, all requirements must be met for conversions. In addition zoning code section 20.390.004 has additional regulations for condominium conversions which are quite stringent and require that a minimum of 33% of the total units be affordable low or moderate-income units, and 15% must be set aside for lower-income units.
3-10A | Monitor and Address Potential Conversion of Subsidized Units to Market Rates | Monitor the supply of subsidized affordable housing to anticipate possible conversions. Publicize State and federal notice requirements to nonprofit developers and property owners of at-risk housing. Respond to any federal and/or State notices including Notice of Intent to Pre-Pay, owner Plans of Action, or Opt-Out Notices filed on local projects. | Currently according to the California Housing Partnership Corporation there are two properties in SSF that are at risk of converting to market rate housing. Given the dissolution of the Redevelopment Agency the City's ability to acquire such at risk units is hampered. However, one of the properties is owned by Rotary International (Rotary Club), a nonprofit organization, that has a motivation to keep the units affordable.
3-10B | Provide Assistance to Maintain Affordability of At-Risk Units | Prioritize Federal, State and Redevelopment Agency funds and support funding applications to preserve at-risk units through acquisition, rehabilitation, or refinancing by nonprofit housing developers. | See Policy 3-10 Achievements above.
3-10C | Assist Tenants Displaced or At-Risk for Displacement from Affordable Housing | Prioritize Federal, State and Redevelopment Agency funds to assist tenants displaced by the conversation of at \-risk units and provide referrals to relevant social service providers for affected tenants. | See Policy 3-10 Achievements above.
Goal 4 Maintain and Improve the Quality of Life
POL 4-1 | Prohibit Residential Development on Environmentally Hazardous Sites | Prohibit new residential development in areas containing major environmental hazards (such as floods and seismic and safety problems) unless adequate mitigation measures are taken. | SSF zoning code section 20.160 provides a Hillside (HS) Overlay District for properties that have an average slope of 15% or more and sets forth specific standards for safe development. In addition zoning code section 20.170 has a Special Environmental Studies (ES) Overlay District that applies to areas of the City that the General Plan identifies as ecology sensitive habits or susceptible to geologic hazards. | There was no Program 4-1A, so I've included the Policy in case the jurisdiction would like to address it in their review. - That said… this particular policy is redundant with program 4-3A.
4-2A | Administer Minimum Building Security Standards | Continue to ensure that all new residential units comply with the Minimum Building Security Standards contained in Chapter 15.48 of the Municipal Code to decrease burglary and other property-related crimes. | All new development applications and additions are routed to both the Police and Fire Departments to ensure that SSFMC Chapter 15.48 is implemented and that security measures are considered during the design process. Specific attention is paid to landscaping to make sure lines of sight are retained.
4-3A | Review Residential Project Sites for Major Environmental Hazards and Prohibit Development on Hazardous Sites | Review residential projects for major environmental hazards during the environmental review process, and prohibit the development of projects on sites containing such hazards unless adequately mitigated. | During the CEQA review process staff looks at all potential hazards to residential development. In addition, the Code Enforcement and Building Divisions both work with property owners to address unsafe building conditions.
4-4A | Require Mitigation Measures for All Housing Development in the 65 to 69 dB CNEL SFO Aircraft Noise Contour | Require an acoustical study conducted by a professional acoustic engineer for all new residential project applications in the 65 to 69 dB CNEL SFO aircraft noise contour. Noise mitigation measures are required to achieve an interior noise level of not more than 45 dB for all new units. | The SSF General Plan is updated to be consistent with the SFO Airport Land Use Plan. Prior to purchase of new homes located in the 65 to 69 CNEL aircraft noise contour area, disclosures are provided to potential buys. There are added restrictions placed on new homes that disclose locations that within the 65 to 69 CNEL aircraft contour. (Disclosures? Plan update? These are different measures than what was in the Policy and Program.) | The policy guiding this program adds other specific measures. It says: Prohibit "new residential or noise sensitive development in the 70 dB+ CNEL areas impacted by SFO operations," and "require avigation [aviation?] easements for new residential development in the area between 65 and 69 dB CNEL SFO noise contours." Should any of this be added to the program description?
Goal 5 Support Development of Special Housing Needs
POL 5-1 | Prioritize Special Needs Housing | Continue to give special attention in housing programs to the needs of special groups, including the disabled, large families, the elderly, and families with low incomes. | The new development at 636 El Camino Real has 20 units set aside for San Mateo County Mental Health clients and onsite case management for those clients. Additionally the development at 636 El Camino Real has 40 three-bedroom units for large families. | There was no Program 5-1A, so I've included the Policy in case the jurisdiction would like to address it in their review. - That said... this particular policy is redundant with most of the programs in this section.
POL 5-2 | Encourage Housing Development for the Elderly | Encourage the development of housing for elderly. | The City has been in discussions with representatives of Rotary Plaza (an existing senior housing complex with 181 units) with regards to a potential new development project for seniors housing. However, the future of these discussions is uncertain at this time given the dissolution of the Redevelopment Agency. | There was no Program 5-2A, so I've included the Policy in case the jurisdiction would like to address it in their review. - That said… this particular policy is redundant with programs 5-3A and 5-4A.
5-3A | Grant Density Bonuses for Senior Housing | With the aim of building 10 senior housing units over the 2007-2014 planning period, continue to grant density bonuses for senior housing projects, allowing up to 50 units per acre. Permit reduced parking requirements as well. | There were 28 SSF seniors served by the City's Minor Housing Repair Program for Seniors in FY 12-13 including the following: Center for Independence of Individuals with Disabilities (CID) served 6 elderly heads of households Rebuilding Together Peninsula (RTP) National Rebuilding Day served 1 elderly head of household Safe @ Home Program served 14 elderly heads of households North Peninsula Neighborhood Services Center (NPNSC) House Helpers served 7 elderly heads of households
5-3B | Fund Minor Housing Repairs for Senior Homeowners | Continue to provide funding for minor repairs of homes owned and occupied by low-income senior citizens. Aim to assist 100 units over the 2007-2014 planning period with repairs include plumbing, electrical, painting, carpentry, roof repairs, and masonry work. | See Policy 5-5 Achievements above.
5-4A | Allow Reduced Parking Requirement for Residential Board and Care Facilities | In order to encourage a range of housing types for seniors, continue to allow reduced parking requirements for residential board and care facilities. | The SSF zoning code allows for requests for parking reductions for senior housing developments and developments near transit.
5-5A | Ensure Development Plans Comply with Accessibility Requirements | Review development plans to ensure consistency with State and federal handicap and accessibility laws, making modifications for accessibility as necessary. | During the review of all new development projects and applications for modifications to existing buildings, the Building Division staff plan checks projects to ensure that all State Accessibly Laws are met in accordance with California Building Code Section 1134B.
5-5B | Ensure Housing Access for People with Disabilities in the Zoning Code and Permit Procedures | Complete a review of its Zoning Ordinance and other development procedures to ensure compliance with fair housing laws and ensure that these regulations do not create a hardship for persons with disabilities. By December 2009, amend its Zoning Ordinance and change permit processing procedures, as needed, to facilitate accessibility for disabled persons. | See Policy 5-5 Achievements above.
5-6A | Modify Housing to Accommodate the Needs of People with Disabilities | Continue to fund programs to modify existing housing units to make them accessible to people with disabilities, with the goal of modifying 125 units during the 2007-2014 period. | The City provides annual grant fund to the Center of Independent of Individual with Disabilities (CID) who has a Housing Accessibly Modification (HAM) Program that provides financial assistance to people that need to made modifications to their home to allow for disabled access.
5-7A | Ensure Equal Housing Access in the City Code | Amend the Municipal Code as necessary to provide individuals with disabilities reasonable accommodation in rules, policies, practices, and procedures to ensure equal access to housing. | The zoning ordinance update in 2010 included the addition of SSFMC section 20.510, Waivers and Modifications, that provides provisions for reasonable accommodations to ensure equal access to housing by allowing the Chief Planner authority to grant relief from zoning requirements.
5-7B | Provide Reasonable Accommodation Information | Provide information on reasonable accommodation for the disabled through a brochure and on the City’s website. | See Policy 5-7 Achievements above.
POL 5-8 | Encourage Affordable Housing for Large Families | Encourage provision of affordable housing suitable for large families. | The recently completed affordable housing development at 636 El Camino Real includes 40 three bedrooms units to accommodate large families. In addition, at pre-application meetings staff discusses providing a range of housing sizes with developers during the planning stages of residential development projects prior to the submittal of a formal application. | There was no Program 5-8A, so I've included the Policy in case the jurisdiction would like to address it in their review.
POL 5-9 | Assist the Homeless and Maintain Operation of an Emergency Shelter | Assist the homeless and those at risk of becoming homeless. At least one site shall remain available in the City for the operation of an emergency shelter. | There is a County run homeless shelter located in South San Francisco on North Access Road. The former Redevelopment Agency regularly fund provided funding to the County for the operation of the shelter. | There was no Program 5-9A, so I've included the Policy in case the jurisdiction would like to address it in their review. - That said… this particular policy is redundant with all the 5-10 programs.
5-10A | Support Continuum of Care Planning | Continue to actively participate in the Continuum of Care planning process in order to address emergency shelter or temporary housing needs. | HCD staff attends regular quarterly Continuum of Care meetings with the County. The City continues to provide referrals to families and individuals for social services including case management and referrals for housing and homeless prevention.
5-10B | Fund Organizations Offering Solutions and Services for the Homeless | Continue to fund non-profit organizations that offer creative solutions to solving homeless and/or provide housing related services for the homeless or at-risk homeless. | See Policy 5-10 Achievements above.
5-10C | Fund Transitional Housing Organizations | Continue to fund organizations that provide transitional housing, with the goal of 200 placements of families and/or individuals between 2007 and 2014. | See Policy 5-10 Achievements above.
5-10D | Support Emergency Shelter Operation | Continue to support the operation of a 90-bed year round homeless shelter within the city limits. | See Policy 5-10 Achievements above.
5-10E | Fund and Provide Referrals to Housing and Homeless Prevent Case Management Organizations | Continue to fund and make referrals to organizations providing social services including case management for housing and homeless prevention. Aim to deliver case management and referrals for 500 individuals and families per year from 2007 to 2014. | See Policy 5-10 Achievements above.
Goal 6 Assure Equal Access to Housing
POL 6-1 | Eliminate Unlawful Discrimination | Work to eliminate all unlawful discrimination in housing with respect to age, race, sex, sexual orientation, marital or familial status, ethnic background, medical condition, or other arbitrary factors. | The City, in conjunction with San Mateo County, Daly City, Redwood City and San Mateo developed the Analysis of Impediments (AI) for Fair Housing Choice. This was developed in 2012 and was adopted by the SSF City Council on May 1, 2013 by Resolution #36-2013. | There was no Program 6-1A, so I've included the Policy in case the jurisdiction would like to address it in their review. - That said… this particular policy is redundant with several programs that follow.
6-2A | Ensure Legal Counsel and Advocacy Assistance for Fair Housing and Landlord-Tenant Cases | Provide access to and referrals to organizations that provide legal counseling and advocacy concerning fair housing laws, rights, and remedies for those who believe they have been discriminated against. Aim to pursue 5 discrimination cases and 10 tenant-landlord cases per year from 2007 and 2014. | The City provides an annual grant to a fair housing service provider using its HOME Administrative funds. For FY 12-13 the City provided funds to Project Sentinel (a fair housing provider and tenant/landlord service organization). Project Sentinel severed 50 SSF residents in 2012. In prior years (2007-2011) the City funded the Legal Aid Society (tenant/landlord services) but due to funding cuts, the City no longer funds this organization.
6-2B | Provide Funding to Address Housing Habitability Cases | Fund organizations that provide counseling on tenant-landlord issues and habitability as well as other general housing assistance, with the goal of pursuing 100 habitability cases per year from 2007 and 2014. | See Policy 6-2 Achievements above.
6-2C | Work with Other Jurisdictions to Update the Impediments to Fair Housing Report | Work with other jurisdictions in the County to periodically update the Analysis of Impediments to Fair Housing in San Mateo County report as a means of identifying impediments and development solutions. | See Policy 6-2 Achievements above.
6-2D | Disseminate Fair Housing Information | Disseminate fair housing information through the City website, in public locations, and through nonprofit organizations serving low-income residents. Brochures will continue to be available in English and Spanish. | See Policy 6-2 Achievements above.
6-2E | Promote and Overcome Impediments to Fair Housing | Fund and work with nonprofit organizations to promote fair housing and to identify and overcome impediments to fair housing. | See Policy 6-2 Achievements above.
Goal 7 Energy Conservation
7-1A | Incorporate Energy and Water Conservation in Residential Rehabilitation | Assist with energy and water conserving modifications and features in 10 residential rehabilitation projects annually. | Staff is currently working on a Green Building Ordinance that is slated for implementation in January 2014. During residential rehabilitation projects, like Rebuilding Together, replacement of appliances/utilities includes energy and water conserving models. (GB Ordinance not mentioned in HE Policies or Programs.)
7-1B | Promote Green Building and Energy Conserving Features | Use the Green X-Ray House and the Green Corp training program to promote green building and energy conserving features in new and existing residential construction. Provide tours to homeowners and homebuilders of the Green X-Ray House, a project funded by the Redevelopment Agency and Community Development Block Grant Recovery funds, in order to provide education about energy saving features and products. Through the Green Corps training program, by 2009, train 12 low income and/or disadvantaged youth to perform energy audits and weatherization of homes and support them to provide services and community education for the remainder of the planning period. | See policy 7-1 Achievements above.
7-2A | Provide Residential Energy Efficiency Information | Provide information to promote the use of passive and active solar systems in new and existing residential buildings in order to meet State residential conservation standards. | The City promotes the use of solar panels. In addition, the staff is currently working on a Climate Action Plan (CAP) that sets forth reduction measures that will apply to residential development. Draft measure 3-5 in the CAP promotes energy information and sharing, and educating the community about energy-efficiency behaviors and construction.
7-3A | Fund the Housing Energy Efficiency Rehabilitation Program | Continue to fund a non-profit organization to conduct home repairs for very low- and low-income owner and renter households and to weatherize homes. 30% of the Energy Efficiency Community Block Grant funds will be used for energy conservation retrofits and weatherization, including an attic insulation program, for 120 homeowners by 2014. | Through our loan and grant programs, the use of weatherization programs is included in part of the overall funding for rehabilitation.
7-4A | Enforce Title 24 and Encourage Additional Energy Conservation Measures | Enforce Title 24 requirements for energy conservation in residential development, and encourage residential developers to employ additional solar access, landscaping, building siting, lot configuration, and street design energy conservation measures. | The CAP will include a reduction measures that encourages the integration of higher-density development and mixed-use development near transit facilities and community faculties, and to reduce the dependents on autos through smart parking practices. In addition, the City continues to implement Title 24 requirements. | Street design? To reduce driving?

## TEMPLATE INSTRUCTIONS
INSTRUCTIONS FOR USING THIS TEMPLATE (& IDIOSYNCHRACIES YOU WILL ENCOUNTER):
1) Goal (or Policy or Theme) Subheaders:
* Each is a combination of 4 rows, all of which are necessary to provide the underline and appropriate spacing. Whenever you need more of these subheader rows, copy ALL FOUR rows and "INSERT COPIED CELLS" (DO NOT "PASTE").
* The row with the text is manually set to 20 points to accomodate 1 line of text. Set it to 30 points if you have 2 lines of text. Do not automatically adjust these row heights.
2) Program Rows:
* These are designed to have their row heights set automatically. If you ever find yourself needing to reestablish the automatic row heights, make sure you DO NOT select the entire worksheet, because this will destroy the heights of the Goal Subheader rows.
* Make sure you don't have any extra spaces or returns after the text in your cells. This will interfere with automatic row heights.
* When you need more of these rows, it's best to either insert rows above them, or copy and "insert copied cells." This will allow you to replicate the cell borders.
3) Last Row: Notice that it is followed by a thick border. Don't delete this row. Always put the text for your last program in this row. If you need to get rid of rows, delete the ones above it.
4) Document Header: Make sure to put in your jurisdiction's name!
5) Column Widths: The total width of all columns is 152 points. The width of these columns affects the size of the text when you print your table. If you must adjust the width of a column, try to compensate by adjusting another column. For instance, if you widen a column from 26 to 31, then you should shrink another column from 48 to 43.